ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Relevant country background	2

1.4.	Current state of affairs in the relevant sector	2

1.5.	Related programmes and other donor activities:	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	3

2.2.	Purpose	3

2.3.	Results to be achieved by the Consultant	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project intervention	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific activities	5

4.3.	Project management	6

5.	LOGISTICS AND TIMING	6

5.1.	Location	6

5.2.	Commencement date & Period of implementation of tasks	6

6.	REQUIREMENTS	6

6.1.	Personnel	6

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the Consultant	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission & approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

NA	9

# BACKGROUND INFORMATION

## Beneficiary country

Romania and Republic of Serbia/ Programme eligible area.

## Contracting Authority

Regional Office for Cross Border Cooperation Timisoara (RO CBC Timisoara)

## Relevant country background

IPA Cross-border Cooperation was created as an essential element of the European Union Instrument for Pre-Accession, intended to prepare candidate countries for future management of EU Structural Funds. In achieving this goal, cross-border cooperation plays a very special role. Under this instrument the EU supports cooperation programmes between Member States and candidate countries, and for the first time also programmes between candidate and potential candidate countries.

IPA Cross-border Cooperation programmes between Member States and accession countries are “a new generation” of external cooperation programmes. All participating partners on all sides of borders use the same rules, implement projects jointly, and manage budgets together. This enables the establishment of long-lasting contacts between people, and joint cross-border activities to help economic development, support small-scale infrastructure, protect the environment, and foster research, culture, and education. It also increases the overall social cohesion along EU external borders. Furthermore, through the process of project identification, applying for funds and project implementation, partners from candidate countries gain valuable experience in management of EU funds. (www.ecd.eu)

The Romania-Republic of Serbia IPA Cross-Border Cooperation Programme is funded by the European Union under the framework of the Instrument for Pre-accession Assistance (IPA CBC), the Cross-border Component and co-financed by the Partner States in the Programme. The Programme focuses on increasing the overall competitiveness of the economy in the Romania-Republic of Serbia border area and on the improvement of the quality of life for the border communities in both countries.

## Current state of affairs in the relevant sector

Territorial cooperation is about supporting local initiatives in regions and cities from different countries in the European Union and beyond. For more than 20 years funding opportunities and technical assistance has been encouraging cooperation projects in all areas affecting our daily life e.g. in transport, education, energy, environment, employment, health care or public safety. As part of the European Cohesion Policy it aims at strengthening economic and social cohesion of the European Union and partner states. Today cooperation affects not only EU member states but is also active at the external border so the border do not represent a “finis terrae” for the population living in these areas. The European Union developed three main instruments to facilitate territorial cooperation in Europe. They provide a framework and fund opportunities to bring people closer, across borders.

- It is important that the general public is made aware of the impact this Programme has had upon the lives of the people in the Romanian and Serbian border area. This will be achieved by organizing a joint promotion activity under the coordination of the RO CBC Timisoara.

## Related programmes and other donor activities:

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part of is as follows:

To achieve on the basis of joint cross-border projects and common actions by Romanian and Serbian stakeholders a more balanced and sustainable socio-economic development of the Romanian-Serbian border area.

## Purpose

The objective of this contract is to improve the visibility of the cooperation between Romania and the Republic of Serbia, to disseminate its outcomes and to show how it has impacted the quality of life for the populations it serves by organising two Final Conferences – a joint communication activity held in the eligible area of the Romania - Republic of Serbia IPA Cross-border Cooperation Programme, one in Serbia and one in Romania.

The purpose of this contract is as follows:

- Organisation of the Final Conference for the Romania -  Republic of Serbia IPA Cross-border Cooperation Programme in Romania;

- Organisation of the Final Conference for the Romania -  Republic of Serbia IPA Cross-border Cooperation Programme in Serbia;

## Results to be achieved by the Consultant

Organizing and ensuring administrative support for the two Final Conferences for the Romania – Republic of Serbia IPA Cross-border Cooperation Programme:

- Organisation of the Final Conference for the Romania -  Republic of Serbia IPA Cross-border Cooperation Programme in Romania:

- Preparing promotional packages containing:

- - 140 personalized document folders (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.)

- - 140 personalized memory sticks – minimum USB 3.0 and 8 Gb memory space (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.),

- - 140 personalized ball-pens (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.).

- Providing a venue appropriate for hosting approx. 100 participants, with catering and conference facilities (projector, laptop, screen, sound system etc.)

- Ensuring protocol arrangements for participants – light catering consisting of coffee, tea, water, soft drinks, sweet and salty pastries etc.

- Providing interpreters/translators for Romanian-Serbian-Romanian (minimum 2 persons) and proper translating equipment.

- Organisation of the Final Conference for the Romania -  Republic of Serbia IPA Cross-border Cooperation Programme in Serbia:

- Preparing promotional packages containing:

- - 140 personalized document folders (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.),

- - 140 personalized memory sticks – minimum USB 3.0 and 8 Gb memory space (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.),

- - 140 personalized ball-pens (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.).

- Providing a venue appropriate for hosting approx. 100 participants, with catering and conference facilities (projector, laptop, screen, sound system etc.)

- Ensuring protocol arrangements for participants – light catering consisting of coffee, tea, water, soft drinks, sweet and salty pastries, etc.

- Providing interpreters/translators for Romanian-Serbian-Romanian (minimum 2 persons) and proper translating equipment.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project intervention

The Consultant will receive the relevant information – content and visibility – from the Contracting Authority and the staff involvement will be ensured.

## Risks

N/A.

# SCOPE OF THE WORK

## General

### 4.1.1 Description of the assignment

The two final conferences of the Programme will be organized by the RO CBC Timisoara in order to promote the results of the Romania – Republic of Serbia IPA Cross-border Cooperation Programme to the general public and celebrate, together with the stakeholders and partners, the successful implementation of this Programme in the eligible area. In this respect, RO CBC Timisoara will ensure:

- the involvement of the staff and beneficiaries from both sides of the border participating in the activities.

The assignment for the Consultant is to organize the promotion activity for both events, in Romania and Republic of Serbia respectively, and to sustain the Contracting Authority in organizing the event. This activity intends to promote the programme and European territorial cooperation in general in a traditional way, an approach targeted at the general public. The message that needs to be put forward is that European territorial cooperation is an instrument which brings people together, across borders, in order to solve common or similar issues that cannot be easily managed within a single country and that cooperation does not stop at the EU borders, because lots of initiatives involve neighbouring countries – like the Republic of Serbia.

### 4.1.2 Geographical area to be covered

Eligible area of the Programme: in Romania – Timis, Caras-Severin and Mehedinti counties; and in Republic of Serbia – North Banat, Central Banat, South Banat, Borski and Branicevski districts.

### 4.1.3 Target groups

The general public, the media representatives, potential applicants and beneficiaries from the eligible area in Romania: Timis, Caras-Severin and Mehedinti Counties and in Serbia: North Banat, Central Banat, South Banat, Borski and Branicevski districts.

## Specific activities

In order for the event to run smoothly, all services will be agreed upon and obtained by the Consultant with the support of the Contracting Authority.

The Consultant will be tasked to ensure the following:

- Activity 1:	Organisation of a Final Conference in Romania

- This activity implies:

- Preparing promotional packages containing:

- - 140 personalized document folders (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.)

- - 140 personalized memory sticks – minimum USB 3.0 and 8 Gb memory space (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.),

- - 140 personalized ball-pens (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.).

- Providing a venue appropriate for hosting approx. 100 participants, with catering and conference facilities (projector, laptop, screen, sound system etc.) – 1 day.

- Ensuring protocol arrangements for participants – light catering consisting of coffee, tea, water, soft drinks, sweet and salty pastries etc.

- Providing interpreters/translators for Romanian-Serbian-Romanian (minimum 2 persons) and proper translating equipment.

- The promotional activities will be done based on the visibility guidelines provided by the Contracting Authority – RO CBC Timisoara.

- The promotional items will be delivered to the public only after the acceptance given by the Contracting Authority on the visibility and content.

- Activity 2: Organisation of a Final Conference in Serbia

- This activity implies:

- Preparing promotional packages containing:

- - 140 personalized document folders (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.)

- - 140 personalized memory sticks – minimum USB 3.0 and 8 Gb memory space (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.),

- - 140 personalized ball-pens (for approx. 100 participants and a reserve of 40 pieces for journalists, other guests etc.).

- Providing a venue appropriate for hosting approx. 100 participants, with catering and conference facilities (projector, laptop, screen, sound system etc.) – 1 day.

- Ensuring protocol arrangements for participants – light catering consisting of coffee, tea, water, soft drinks, sweet and salty pastries etc.

- Providing interpreters/translators for Romanian-Serbian-Romanian (minimum 2 persons) and proper translating equipment.

- The promotional activities will be done based on the visibility guidelines provided by the Contracting Authority – RO CBC Timisoara.

- The promotional items will be delivered to the public only after the acceptance given by the Contracting Authority on the visibility and content.

Activity 3:  Reporting

The Consultant will submit an Inception Report at the beginning of the contract, Interim Reports after completing each task, Draft Final Report before the end of the period of implementation of tasks and a Final Report, according to art.7 of present Terms of Reference.

The interim reports can be submitted by the Consultant after each task, but they must be approved by the Contracting Authority prior to issuing the invoices. In order for the payment to be made, invoices must be accompanied by the approved interim reports.

The final payments will be made until the 31st of December 2016.

The services will be contracted for a period of approx. 5 months, beginning with the 1st of July 2016 (the estimated date of signing the contract), and the offer is to be made for lump sum for the complete services.

The Consultant will perform these services no later than 30th of November 2016.

## Project management

### 4.3.1 Responsible body

The Financial, Accounting and Administrative Department and the Joint Technical Secretariat/Joint Secretariat within the Regional Office for Cross-Border Cooperation Timisoara will be responsible for managing the contract.

### 4.3.2 Management structure

The management structured of the Regional Office for Cross-Border Cooperation Timisoara is:

-Executive Director

-Internal audit

-Economic Director

-Joint Technical Secretariat Department

-First Level Control Unit

-Human Resources and Communication Office

-Financial, Accounting and Administrative Department

### 4.3.3 Facilities to be provided by the Contracting Authority and/or other parties

NA

# LOGISTICS AND TIMING

## Location

The location of the operational base for the project will be in Timisoara, Romania.

The actual location of the events will be in the eligible area of the Romania-Republic of Serbia IPA CBC Programme: one location in Romania and one location in Serbia.

## Commencement date & Period of implementation of tasks

The intended commencement date is the 1st of July 2016 and the period of implementation of the contract will be until the 30th of November 2016.

# REQUIREMENTS

## Personnel

This Terms of Reference contains expert profiles and the tenderer shall submit CVs and Statement of Exclusivity and Availability for the key experts.

### 6.1.1 Key experts

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Team Leader

Qualifications and skills

  - University Degree;

  - Romanian and English language fluency;

  - Communication skills;

  - Computer skills - Knowledge of word processing software and Internet.

General professional experience

  - Minimum of 3 years of work experience.

Specific professional experience

  - Participation in organising events and promoting them.

Key expert 2: Assistant

Qualifications and skills

  - University Degree;

  - Romanian and English language fluency;

  - Computer skills - Knowledge of word processing software and Internet.

General professional experience

  - Minimum of 1 year of work experience.

Specific professional experience

  - Participation in organising events and ensuring the logistics.

### 6.1.2 Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender. The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Consultant.

## Facilities to be provided by the Consultant

The Consultant shall ensure that experts are adequately supported and equipped. In particular it shall ensure that there is sufficient administrative and logistical provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support its activities under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority as part of this service contract or transferred to the Contracting Authority at the end of this contract. Any equipment related to this contract which is to be acquired by the beneficiary country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The consultant will submit the following reports in English in one original and one copy:

- Inception Report of maximum 12 pages to be produced after 1 week from the commencement of the implementation. In the report the consultant shall describe e.g. the first findings, the progress in collecting data, the encountered and/or foreseen difficulties in addition to the work programme and staff mobilization. The consultant is advised to proceed with his/her work also in absence of comments by the Contracting Authority to the inception report.

- Interim reports of minimum 5 pages. The Consultant can prepare interim reports after providing the services according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments as indicated in the Special Conditions.

- Draft final report of maximum 12 pages (main text, excluding annexes). This report shall be submitted after the finalization of the activities.

- Final report with the same specifications as the draft final report, incorporating any comments received from the concerned parties on the draft report. The final report shall be provided by the latest 2 days after the reception of the comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to permit an informed decision on services provided. The detailed analyses which underlie the mission's recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice. This final report must be approved by the Contracting Authority.

## Submission & approval of reports

The reports referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference”.

## Special requirements

## NA