ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	3

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	4

3.	ASSUMPTIONS & RISKS	5

3.1.	Assumptions underlying the project	5

3.2.	Risks	5

4.	SCOPE OF THE WORK	5

4.1.	General	5

4.2.	Specific work	10

4.3.	Project management	11

5.	LOGISTICS AND TIMING	12

5.1.	Location	12

5.2.	Start date & Period of implementation of tasks	12

6.	REQUIREMENTS	12

6.1.	Staff	12

6.2.	Office accommodation	16

6.3.	Facilities to be provided by the Contractor	16

6.4.	Equipment	16

7.	REPORTS	16

7.1.	Reporting requirements	16

7.2.	Submission and approval of reports	17

8.	MONITORING AND EVALUATION	17

8.1.	Definition of indicators	17

8.2.	Special requirements	17

# BACKGROUND INFORMATION

## Partner country

Romania

## Contracting Authority

Regional Office for Cross Border cooperation Timisoara

## Country background

The Interreg - IPA CBC Romania – Serbia Programme has been prepared in line with the Regulation (EU) No 231/2014 of the European Parliament and of the Council of 11 March 2014 establishing an Instrument for Pre-accession Assistance (IPA II) (hereafter referred to as the “IPA Regulation”), Regulation (EU) No 236/2014 of the European Parliament and of the Council of 11 March 2014 laying down common rules and procedures for the implementation of the Union's instruments for financing external action, Commission implementing regulation (EU) No 447/2014 of 2 May 2014 on the specific rules for implementing Regulation (EU) No 231/2014 of the European Parliament and of the Council establishing an Instrument for Pre-accession assistance (IPA II) (hereafter referred to as the “IPA Implementing Regulation”). The Programme is the result of a co-operative effort by the Romanian and Serbian national, regional and local authorities.

The Romania-Republic of Serbia IPA Cross-border Cooperation for 2007-2013 programming period, the 2003 Phare External Border Initiative Programme for Romania and the Neighbourhood Programme Romania- Serbia & Montenegro 2004-2006 paved the way for the new integrated cross-border instrument to be implemented at EU external borders as of 2007, therefore conditions for cross-border cooperation are already in place and this IPA Cross-Border Cooperation Programme can concentrate on its strategic goal of achieving a more balanced sustainable socio-economic development of the Romania-Republic of Serbia border area.

## Current situation in the sector

The Interreg - IPA CBC Romania – Serbia Programme provides the opportunity for both countries to continue their cross-border cooperation under the new instrument. The analysis set out in the Programming Document shows that even if there is very uneven economic development within the border area, this area of cooperation is characterized by similar agricultural, economic and industrial assets on both sides of the border, and thus common challenges can and should be tackled in part by joint actions.

The programme strategy focuses on the key challenges of the border region and the responses that are available to address problems that exist, namely:

- Overcoming specific issues related to the connectedness of the region, both internally between the border regions, and crucially also externally between the border region and neighbouring areas

- Tackling the lack of competitiveness which is a common issue affecting the economy of the border area as a whole, with negative impacts in both the Romanian and Serbian border areas. This includes issues such as entrepreneurship and business activity, innovation, and levels of investment

- Addressing key issues of rural development which are characteristic of the regions on both sides of the border, and which would benefit from joint cross-border action in relation to key areas such as (inter alia) agriculture, rural tourism development, and specific labour market challenges in rural areas.

- Dealing with the significant common challenges in the environment and in specific aspects of local/regional preparedness in relation to cross-border emergency situations

- Overcoming the border as a perceived “division”, and promoting greater cooperation and contact between regions and communities on both sides of the border

## Related programmes and other donor activities

NOT APPLICABLE

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

LOT 1:

The aim of the assignment is to support the Evaluation Committee in the Technical and financial evaluation and state aid incidence assessment of project proposals submitted in response to Romania – Serbia INTERREG IPA Cross Border Cooperation Programme call for proposals for ordinary projects, with deadline 1st of February 2016.

LOT 2:

The aim of the assignment is to support the Evaluation Committee in the Technical and financial evaluation and state aid incidence assessment of project proposals submitted in response to Romania – Serbia INTERREG IPA Cross Border Cooperation Programme call for proposals for strategic projects, with deadline 15th of March 2016.

## Purpose

The purpose of this contract is as follows:

LOT 1:

- To provide support to the Evaluation Committee voting members by contracting external assessors that will perform the technical and financial evaluation  for every project proposal submitted in response to Romania – Serbia INTERREG IPA Cross Border Cooperation Programme call for proposals for ordinary projects, with deadline 1st of February 2016. The external assessors will present detailed arguments supporting the average points they gave for every criterion in the grid, also, specifying the page number where the information supporting the arguments may be found, if applicable.

- In order to meet the requirements of the European Commission and in order to allow a smooth implementation of the Programme and its approved projects, in the framework of Interreg - IPA CBC Romania – Serbia Programme, State Aid incidence assessment will be performed in accordance with the Guidelines for applicants’ requirements. The state aid incidence assessment will be performed in parallel with the technical and financial evaluation. State aid incidence assessment shall be performed by the external assessors, with proven experience in state aid discipline, based on the specific state aid compliance grid Evaluation grid for State aid compliance check (State aid compliance check-list) that is set forth in the Applicant’s Guide.

- LOT 2:

- To provide support to the Evaluation Committee voting members by contracting external assessors that will perform the technical and financial evaluation  for every project proposal submitted in response to Romania – Serbia INTERREG IPA Cross Border Cooperation Programme call for proposals for strategic projects, with deadline 15th of March 2016. The external assessors will present detailed arguments supporting the average points they gave for every criterion in the grid, also, specifying the page number where the information supporting the arguments may be found, if applicable. In order to meet the requirements of the European Commission and in order to allow a smooth implementation of the Programme and its approved projects, in the framework of Interreg - IPA CBC Romania – Serbia Programme, State Aid incidence assessment will be performed in accordance with the Guidelines for applicants’ requirements. The state aid incidence assessment will be performed in parallel with the technical and financial evaluation. State aid incidence assessment shall be performed by the external assessors, with proven experience in state aid discipline, based on the specific state aid compliance grid Evaluation grid for State aid compliance check (State aid compliance check-list) that is set forth in the Applicant’s Guide.

## Results to be achieved by the Contractor

LOT 1 and LOT 2:

The tasks to be accomplished by the external assessors consist of the technical and financial evaluation of project proposals.

The expert tasks include the following:

- acquaintance of relevant programme documents (e.g. Romania – Serbia INTERREG IPA Cross Border Cooperation Programme, Applicant’s Guide for the respective call for proposals available on the Programme’s website , national and European law etc.)

- participation in a clarifications meetings with the Evaluation Committee

- technical and financial evaluation of project proposals according to assessment criteria provided in the Evaluation Grid(s).

- appraisal of each criterion with a score accompanied by a clear qualitative statement in English language (highlighting the strengths and weaknesses of the project proposal) justifying the given score as well as providing assessment conclusions per criterion. In case of recommending a project proposal for funding, also recommendations for necessary amendments during the negotiation phase should be provided by the expert. If needed, experts have to ensure their availability to discuss their assessment with the Evaluation Committee in the frame of the harmonisation of assessments.

- The assessment work carried out by the expert is to be performed through the filling-in of one Evaluation grid for each project proposal assessed.

Moreover, The State Aid expert will analyse the State Aid incidence in accordance with the Guidelines for applicants’ requirements. State aid incidence assessment shall be performed based on the specific state aid compliance grid Evaluation grid for State aid compliance check (State aid compliance check-list) that is set forth in the Applicant’s Guide.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The project evaluation and selection criteria which were prepared by the Managing Authority, together with the National Authority and the Joint Secretariat, are approved by the Joint Monitoring Committee and are available to potential partners being included in the Applicant’s Guide.

The Evaluation committee is formed of a chairperson, a secretary and 6 voting members proposed by the participating countries and will review the conclusions of the external (independent) assessors contracted through this procedure.

External assessors: independent external experts that will work in camera under the supervision of the Chairperson, assisting in a confidential, fair and equitable way the evaluation of the proposals. The role of external assessor is incompatible with being a member, observer in the Joint Monitoring Committee, with the quality of applicant or partner in any of the programme’s previous calls for proposals, as well as, with the quality of performing consultancy or any other programme or project related services in the framework of the Programme to any third parties.  The external assessors will sign a Declaration of Impartiality and Confidentiality before starting the evaluation process. The external assessors of the Evaluation Committee for the Technical and Financial Evaluation and of the Complaint Panel for the technical and financial check phase  have legal responsibilities regarding the final result of the evaluation and will be fully legal responsible in case of a legal proceedings. Moreover, at any moment in time during programme implementation, the Contracting Authority, based on the signed contract, can turn against the external assessors from the Evaluation Committee in order to recover damages related to the Technical and Financial Evaluation, damages resulted/irregularities following an internal or external audit, if those damages/irregularities are proven to be the results of their performance.

## Risks

The use of independent evaluators is not completely risk-free.  A deficient evaluation process (failure to provide the evaluation grids within the deadlines provisioned by the procedures or to provide clear remarks, observations and recommendations) may have a clear impact in a poor evaluation of the project proposals, and consequently this will affect the implementation of projects and slow-down the overall programme implementation and decommitment targets.

# SCOPE OF THE WORK

## General

### Description of the assignment

The technical and financial evaluation phase will be performed as follows:

Step 1: Technical and financial evaluation and state aid incidence assessment

This second phase of the evaluation session for projects submitted within the call for proposals within the Programme will be performed in camera at the premises of Regional Office for Cross Border Cooperation in Timisoara.

The Evaluation Committee, including the external assessors, gathers at the date, hour and location, stipulated in the Invitation received from the JS. Not attending the Evaluation Committee meeting at the date, hour and location stipulated in the JS Invitation will lead to the exclusion of the respective external assessor from the Evaluation Committee for the respective evaluation session and his/hers replacement.

The technical and financial evaluation implies the careful examination of the contents of every application form, the support documents and their technical and financial Annexes by two external assessors. The external assessors shall check, for every project proposal, the fulfilment of the evaluation criteria and the registration of the project expenses in the eligible expenses categories, as these are indicated in the Applicant’s Guide relating to the relevant priority axis and in the grid for the technical and financial evaluation.

The technical and financial evaluation for every project proposal will be performed by completing the technical and financial grid by granting the appropriate points for the situation resulted after the evaluation. The technical and financial evaluation grid is set forth in the Applicant’s Guide for the relevant call for proposal.

Each external assessor shall fill in a technical and financial evaluation grid for every project proposal. The external assessors will present detailed arguments supporting the average points they gave for every criterion in the grid, also, specifying the page number where the information supporting the arguments may be found, if applicable. Moreover, the technical and financial evaluation grid will indicate on every page the name and the title of the external assessor that carried out the evaluation, being signed and dated on every page by that external assessor.

In order to meet the requirements of the European Commission and in order to allow a smooth implementation of the Programme and its approved projects, in the framework of Interreg - IPA CBC Romania – Serbia Programme, State Aid incidence assessment will be assessed in accordance with the Guidelines for applicants’ requirements.

The state aid incidence assessment will be performed in parallel with the technical and financial evaluation.

State aid incidence assessment shall be performed by the external assessors, with proven experience in state aid discipline, based on the specific state aid compliance grid Evaluation grid for State aid compliance check (State aid compliance check-list) that is set forth in the Applicant’s Guide. In case a project undergoing evaluation is suspected of falling under the state aid provisions, the EC may inform in 3 working days from the detection of the situation the MA regarding the project observing the confidentiality of the evaluation process. The MA shall perform the consultation with the relevant authorities to confirm or infirm the suspicion of state aid incidence for the respective operation and inform the EC as soon as possible regarding its findings, if needed.

If a project is subject to state aid it will be rejected, as according to the Applicant’s Guide state aid is not permitted. The comments and arguments for rejection mentioned in the Evaluation grid for State aid compliance check (State aid compliance check-list) and Technical and Financial Evaluation will be presented to the Evaluation Committee. The final decision shall be made by the EC and shall be included in the Technical and Financial evaluation and state aid incidence assessment report.

If a project is rejected based on state aid assessment, the decision cannot be further appealed.

Step 2: Clarification Requests

If, during the technical and financial evaluation process, after the complete examination of the project proposal and the appropriate grid, the external assessors of the EC consider that, for a better assessment of the project proposal, certain clarifications are required in relation to the technical and financial information and Annexes included in the application, then, the Committee will request by means of a written notification sent by fax to the Lead Beneficiary all the necessary information. The letter requesting the clarifications will be signed by the Chairperson, after its contents has been agreed by the two external assessors. The letter will compulsory contain the response deadline, which will be jointly agreed by the members of the evaluation team, without exceeding maximum 10 working days from the date of sending the letter.

During the evaluation, depending on the complexity of the clarifications requested, the EC may decide to give an extended deadline for submitting the clarifications.

All correspondence regarding the clarifications shall be annexed to each of the files of the financing request and will be annexed to the contracts prepared by the JS and send to MA.

In case the technical and financial adequacy cannot be judged properly or if deficiencies are identified the assessors have the right to request an answer from the Applicant via the EC Chairperson. The assessor may request clarifications only one time during the assessment process. The assessors shall not have any direct contact with the Applicant. The Chairperson/Secretary shall collect all clarifications from the assessors per each application and prepare the request for clarifications.

The maximum number of the clarification requests that can be allowed for a single project proposal during the technical and financial verification phase is 1. Additional clarifications letter are not permitted in the phase 2, with the exception of state aid incidence assessment.

If the Lead Beneficiary fails to send the response to the clarification request by the deadline set by the EC or if the response does not provide the expected clarifications, the answer will not be taken into consideration and the results will be properly indicated in the technical and financial evaluation grids, only according to the existing information.

Step 3: Clarification check;

The secretary of EC provides external assessors as soon as possible the clarification received from the applicant. They verify the clarification and finish the evaluation grid in maximum 5 working days.

Step 4: Technical and financial report

After the examination of all the project proposals from the technical and financial evaluation phase, the EC elaborates the Technical and Financial Evaluation and state aid incidence assessment Report.

The technical and financial evaluation report shall underline the arguments that led to the decision to grant a certain number of points to each project proposal for the technical and financial evaluation phase and include the list of project proposals ranked according to the scores given by the external assessors. Such report will be signed by every voting member, the EC chairperson and secretary, and shall have attached the individual technical and financial grids signed on every page by the external assessors.

If there are differences exceeding 10 points between the points granted by the pair of external assessors, a EC meeting will take place. The minutes of the meeting and the conclusions and results will be included in Technical and Financial Evaluation Report.

During the technical meeting mediated by the Chairperson of the EC, the external assessors will present their arguments upon which they awarded their score to the voting members. The Chairperson of the EC will make sure that the two external assessors assigned for the project have the possibility to present their arguments and that these arguments are supported by the project proposal. After the technical meeting, if the difference of more than 10 points remains, the EC will request for re-evaluation of the respective Application Form by a new team of two external assessors.

The Chairperson of the Evaluation Committee is responsible for supervising the technical meeting, will ensure the access to the originals of the project proposals in question and the applicant’s answers to the clarification letters sent by the EC.

The conclusions after such discussions will be underlined in the Technical and Financial Evaluation Report.

The Technical and financial phase shall be successfully completed by filling in Technical and Financial Evaluation Report, where the arguments that supported the decision to accept or to reject the Application Forms shall be detailed.

The projects proposed for financing are those projects which have obtained the minimum score required according to the Applicants Guide in the technical and financial evaluation and whose budgets contain eligible expenses which do not exceed the limit set forth for the respective call.

The projects which have scored less than the minimum number of points provisioned in the Applicants Guide for the conformity with the programme and for other criteria (from 1 to 6 in the technical and financial compliance grid) are considered rejected.

Once the voting members of the EC have agreed on the outcome of Step 2, the report and the minutes of the EC meeting are signed by all members of the Committee (voting and non-voting) and the Technical and Financial Evaluation Report is submitted to the MA for approval for the 2nd step of the evaluation procedure. The MA will verify on a sample basis whether the evaluation process took place according to the regulations and provisions in force, identifying any possible irregularities/ deficiencies in the procedure and informing the JMC accordingly.

The MA may perform random checks of individual project applications and their assessment in order to verify the effectiveness and correctness of the evaluation procedure. In case discrepancies occur, MA makes necessary provisions to clarify the situation or possible reasons.

The Complaint Panel for the technical and financial phase

The Complaint Panel is the only body entitled to review a complaint against a decision regarding assessment of projects in the technical and financial phase.

The members of the Complaint Panels for the technical and financial check phase are appointed by the Managing Authority (subject for the approval of the Head of MA and NA) based on proposals of the Chairperson of the Evaluation Committee, from the external assessors previously selected by public procurement procedure. The Complaint Panel will consist in 3 members, other than the ones who initially evaluated the project proposal.(Annex 6)

The Complaint Panel comprises of 3 external assessors other than the ones who initially evaluated the project proposal. There may be several Complaint Panels appointed, depending on the number of complaints received.

The Complaint Panel for the technical and financial phase will be appointed only if complaints are received following the technical and financial check phase.

Within 3 working days after the receipt of the complaint the JS confirms to the Lead Beneficiary in writing having received the complaint and notifies the Managing Authority. The complaint will then be examined on the basis of the information brought forward by the Complaint Panel for the technical and financial phase.

The JS shall provide the Complaint Panel for the technical and financial phase no later than 5 working days after the receipt of the complaint with a copy of:

- the complaint;

- the original application form and all supporting documents that were taken into consideration by the relevant bodies during the project assessment process;

- all documents relating to the assessment of the application in question including checklists and the record of the  Evaluation Committee decision;

- if applicable, correspondence and all documents received within clarifications

- any other document requested by the Members of the Complaint Panel relevant to the complaint.

The decision if the complaint is justified or to be rejected is taken by the Complaint Panel for the technical and financial check phase by consensus and if this is not possible to be reached, by qualified majority. In case it is justified, the project proposal will be reassessed, and new scores can be awarded.

If the appeal is rejected, JS shall notify the LB and the MA regarding the result of the appeal analysis.

The appeals and their results shall be mentioned in the consolidated final evaluation report.

The decision is final, binding to all parties and not subject of any further complaint proceedings within the Programme based on the same grounds and in the same Phase of the procedure.

The external assessors of the Evaluation Committee for the Technical and Financial Evaluation and of the Complaint Panel for the technical and financial check phase  have legal responsibilities regarding the final result of the evaluation and will be fully legal responsible in case of a legal proceedings. Moreover, at any moment in time during programme implementation, the JS, based on the signed contract, can turn against the external assessors from the Evaluation Committee in order to recover damages related to the Technical and Financial Evaluation, damages resulted/irregularities following an internal or external audit, if those damages/irregularities are proven to be the results of their performance.

The complaint procedure – from the receipt of the complaint by the JS to the communication to the Lead Partner of the Complaint Panel’s decision – should be resolved and communicated within maximum 30 calendar days.

### Geographical area to be covered

### The eligible area of the Romania-Serbia IPA Cross-Border Cooperation Programme is:

### •	Romania: Timis, Caras-Severin and Mehedinti counties

### •	Serbia: North Banat, Central Banat, South Banat, Branicevski, Borski and Podunvski districts.

### Target groups

The primary target group is represented by specialists with experience in the evaluation of projects submitted under various European Union grants, especially cross-border cooperation grants.

The secondary target group is represented by the applicants who have submitted projects under the first call for proposals, since their projects will be evaluated by the Evaluation Committee.

## Specific work

External Assessors will be appointed for each project proposal by the Chairperson, Secretary and voting members of the Evaluation Committee. Each proposal should be assessed independently by two external assessors working separately on “four eyes” principle and producing their own independent assessment. The Chairperson together with the voting members will attribute applications to assessors matching the content of each proposal with their field of expertise.

To ensure the independence of the technical and financial evaluation and state aid compliance to be performed in her/his capacity as “external assessor”, prior to the signature of the contract the selected expert will have to sign a declaration certifying that there is no conflict of interest at the time of contracting and that she/he undertakes to inform the Evaluation Committee if any conflict should arise in the course of the assessment.

A conflict of interest exists if the impartial and objective function of an assessor is compromised for reasons involving family, emotional life or political affinity, economic interest or any other shared interest with the project applicants. Throughout the assessment process, and during five years following the completion of the assignment, the expert must ensure the confidentiality of the information and documents. This shall be certified by the selected expert by signing a Declaration of Impartiality and Confidentiality.

A number of 193 project applications have been submitted under the call for proposals. The technical and financial evaluation for every project proposal will be performed by completing the technical and financial grid by granting the appropriate points for the situation resulted after the evaluation. The evaluation grid is set forth in the Applicant’s Guide of the call for proposals (the Applicant Guide can be downloaded from the Programme website www.romania-serbia.net

The external assessors shall check, for every project proposal, the fulfilment of the evaluation criteria, as these are indicated in the Applicant’s Guide relating to the relevant priority axis and in the grid for the technical and financial evaluation.

Each project proposal will be individually evaluated from the technical and financial point of view (without checking the State Aid incidence) by 2 external assessors.

If, during the technical and financial evaluation process, after  completing examination of the project proposal and the appropriate grid, the evaluators of the Evaluation Committee consider that, for a better assessment of the project proposal, certain clarifications are required in relation to the technical and financial information and Annexes included in the application, then, the Committee will request by means of a written notification sent by fax to the Lead Partner all the necessary information. The letter requesting the clarifications will be signed by the Chairperson, after its contents has been agreed with the voting members and with the two external assessors.

In order to meet the requirements of the European Commission and in order to allow a smooth implementation of the Programme and its approved projects, in the framework of Interreg - IPA CBC Romania – Serbia Programme, State Aid incidence assessment will be assessed in accordance with the Guidelines for applicants’ requirements.

The state aid incidence assessment will be performed in parallel with the technical and financial evaluation.

State aid incidence assessment shall be performed by the external assessors, with proven experience in state aid discipline, based on the specific state aid compliance grid Evaluation grid for State aid compliance check (State aid compliance check-list) that is set forth in the Applicant’s Guide. In case a project undergoing evaluation is suspected of falling under the state aid provisions, the EC may inform in 3 working days from the detection of the situation the MA regarding the project observing the confidentiality of the evaluation process. The MA shall perform the consultation with the relevant authorities to confirm or infirm the suspicion of state aid incidence for the respective operation and inform the EC as soon as possible regarding its findings, if needed.

If a project is subject to state aid it will be rejected, as according to the Applicant’s Guide state aid is not permitted. The comments and arguments for rejection mentioned in the Evaluation grid for State aid compliance check (State aid compliance check-list) and Technical and Financial Evaluation will be presented to the Evaluation Committee. The final decision shall be made by the EC and shall be included in the Technical and Financial evaluation and state aid incidence assessment report.

If a project is rejected based on state aid assessment, the decision cannot be further appealed.

## Project management

### Responsible body

The Financial, Accounting and Administrative Department of the Regional Office for Cross-Border Cooperation Timisoara will be responsible for managing the contract.

### Management structure

- Executive Director

- Internal audit

- Legal Adviser

- Economic Director

- Joint Secretariat Department

- First Level Control

- Human Resources Office and Communication

- Financial, Accounting and Administrative Department

### Facilities to be provided by the Contracting Authority and/or other parties

The Contracting Authority will ensure the office space in Timisoara at the headquarters of the Regional Office for Cross-Border Cooperation Timisoara, where the Evaluation Committee will perform its activity.

The office will be equipped with basic furniture,essential IT peripheral (printers, photocopy machine, access to fax machine), wireless internet connection and stationary.

# LOGISTICS AND TIMING

## Location

The tasks will be performed in camera, at the headquarters of the ROCBC Timisoara, in no. 5, Proclamatia de la Timisoara Street, code 300054, Timisoara, Timis County, Romania.

## Start date & Period of implementation of tasks

LOT 1:

The intended start date is 21.03.2016 and the period of implementation of the contract will be 9 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

LOT 2:

The intended start date is 21.03.2016 and the period of implementation of the contract will be 12 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as external experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability.

LOT 1:

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: External assessor for technical and financial evaluation (8 positions)

Qualifications and skills

- university degree in Economics, Law, Engineering, civil engineering, architecture or related subject relevant for this project (at least 2 Key experts must have university degree in Engineering, Civil engineering, architecture or relevant technical degree)

- excellent spoken and written English, demonstrated through the previous activities or through a certification, presented in CV, knowledge of languages of the eligible territory will be considered an added advantage

- have excellent analytical and evaluation skills

- excellent computer skills.

General professional experience

- have at least 5 years professional experience (following the award of the university degree) acquired in positions related to one or more thematic fields of the programme priorities and programme specific objectives;

or

- at least 2 Key experts must have at least 5 years professional experience in technical fields related to construction works (engineering, technical design, etc.)   in order to evaluate the projects which have infrastructure component.

Specific professional experience

- at least 3 completed assignments as an assessor / evaluator in the context of Structural Funds and/or other financial instruments;

- have proven experience in cohesion policy and/or European territorial cooperation;

- one of the experts must have at least 1 completed assignment as a Team Leader in projects funded by EU funds/other financial instruments;

Key expert 2: State Aid Expert (2 positions)

Qualifications and skills

- university degree in Economics, Law, Engineering, civil engineering, architecture or related subject relevant for this project

- excellent spoken and written English, demonstrated through the previous activities or through a certification, presented in CV

- have excellent analytical and evaluation skills

- excellent computer skills.

General professional experience

- Have at least 5 years of professional experience, following the award of the university degree, in state aid discipline

Specific professional experience

- Have a proven experience in the application of the state aid discipline as well as knowledge of judgments provided by the European Court of Justice. Experience in the application of the state aid discipline in the framework of European Territorial Cooperation programmes would be an advantage;

- Have a good knowledge of EU programmes and in particular of programmes funded within Structural Funds;

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

LOT 2:

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: External assessor for technical and financial evaluation (4 positions)

Qualifications and skills

- university degree in Economics, Law, Engineering, civil engineering, architecture or related subject relevant for this project (two experts must have university degree in Engineering, Civil engineering, architecture or relevant technical degree)

- excellent spoken and written English, demonstrated through the previous activities or through a certification, presented in CV, knowledge of languages of the eligible territory will be considered an added advantage

- have excellent analytical and evaluation skills

- excellent computer skills.

General professional experience

- have at least 5 years professional experience (following the award of the university degree) acquired in positions related to one or more thematic fields of the programme priorities and programme specific objectives;

or

- two Key experts must have at least 5 years professional experience in technical fields related to construction works (engineering, technical design, etc.) in order to evaluate the projects which have infrastructure component.

Specific professional experience

- at least 3 completed assignments as an assessor / evaluator in the context of Structural Funds and/or other financial instruments;

- have proven experience in cohesion policy and/or European territorial cooperation;

- one of the experts must have at least 1 completed assignment as a Team Leader in projects funded by EU funds/other financial instruments;

Key expert 2: State Aid Expert (1 position)

Qualifications and skills

- university degree in Economics, Law, Engineering, civil engineering, architecture or related subject relevant for this project

- excellent spoken and written English, demonstrated through the previous activities or through a certification, presented in CV

- have excellent analytical and evaluation skills

- excellent computer skills.

General professional experience

- Have at least 5 years of professional experience, following the award of the university degree, in state aid discipline

Specific professional experience

- Have a proven experience in the application of the state aid discipline as well as knowledge of judgments provided by the European Court of Justice. Experience in the application of the state aid discipline in the framework of European Territorial Cooperation programmes would be an advantage;

- Have a good knowledge of EU programmes and in particular of programmes funded within Structural Funds;

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contracting Authority.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

The Consultant shall ensure to the experts the following:

- travel costs to the headquarters and from the headquarters of the Evaluation Committee (sustained by the Joint Secretariat of the Regional Office for Cross-Border Cooperation Timisoara, Romania no. 5 Proclamatia de la Timisoara Street, code 300054, Timisoara);

- accommodation according to the Romanian legislation (no more than a 3 star hotel) for the period of evaluation process;

- subsistence (food) expenses.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and one copy:

- Inception Report of maximum 12 pages to be produced after 2 weeks from the start of implementation. In the report the Contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The Contractor should proceed with his/her work unless the Contracting Authority sends comments on the inception report.

- Draft final report of maximum 15 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on tasks performed. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Quantitative Indicators:

- No. of projects effectively assessed / No. of projects assigned to be assessed

Qualitative Indicators:

- The number of projects identified with errors not observed by the Key experts during the evaluation (eg. Evaluation grids not correctly filled in, signed or dated; mathematical errors in the budgets not observed by the Key experts, ineligible expenditures/ activities in the projects not observed by the Key experts, etc.)

## Special requirements

In case of further clarifications are asked for by the Evaluation committee, Managing Authority and Joint Monitoring Committee further tasks shall be carried out within the framework of the present contract accordingly. All the experts should be available for consultations, clarifications and revising the documents during the entire period of evaluations, until the finalisation of the selection process and approval of the list of successful projects, and reserve list, if applicable. The external assessors will have to attend the meetings that will take place either in Romania (Timisoara). Furthermore, the external assessors will have to attend meetings of the Joint Monitoring Committee, if requested.