## REIMBURSEMENT OF EXPENSES GUIDELINES

- In order to reimburse the eligible expenditures of an operation, the Partners request the control from the controllers, within maximum three months period before the Lead partner submits a reimbursement claim in hard copy and electronic version accompanied by a progress report to the JTS. The model of the reimbursement request and the list of requested documents is provided by the MA and is mandatory. The expenditures are reported in LEI/RSD, according to the currency that was used for payment using the Inforeuro exchange rate from the month the partner submitted its expenditures for verifications to the controller.

- Before requesting the reimbursement, the respective expenses must be done, paid and controlled by the first level controller.

- The first level controllers shall verify the reality, legality and the conformity of the expenditures made by the partners after receiving the request for the control. The verification is done on the basis of the requested documentation, annexed to the control claim. The original documents on the basis of which the expenditures are registered in the accounting system of the Partner shall mention the code of the operation. Also, at the request for control, based on a risk analysis of operations, the controllers shall perform on-the-spot visits.

- After the verification of the partners’ supporting documents attached to the reimbursement claim, the Lead Partner will centralize all the documents and submit them to JTS, together with the control reports.  The consolidated reimbursement claim issued by the Lead Partner will contain the following documents: progress report, the reports issued by the first level controllers, reimbursement claim and supporting documents. Considering the fact that the partners have the obligation to submit all the documents to the Lead Partner with at least 15 working days before the deadline, this period represents the interval for the Lead Partner to centralize all the documents and to submit the reimbursement claim.

- The JTS shall receive and verify the reimbursement claim sent by the Lead Partner in maximum 30 days from its submission. The JTS may request clarifications, modifications or other additional information are needed, data that must be provided by the Lead Partner in maximum 5 working days from the request.

- The MA shall verify the reimbursement claim in maximum 30 days from the registration date in MRDT.

- The MA shall make the payment of the reimbursement claim in the account of the Lead Partner indicated in the reimbursement claim in maximum 10 days from the approval of the reimbursement claim by the MA. The payment date is considered to be the date of the bank transfer from the MA account to the Lead Partner account.

- The payments are made in euro, at the Inforeuro exchange rate from the month during which the expenditure was submitted by the final beneficiary to the first level controllers.

- The reimbursement claim has to be related to a progress report, according to the model provided by the MA.

- The obligation of the Lead Partner to submit the progress report, on a three-month basis or at any time the MA/JTS expressively requests so, is maintained even if no expenditures were incurred.