MIS-ETC Code ............

Subsidy contract

from IPA

No………../……….

The following subsidy contract between

Ministry of Regional Development and Tourism

17 Apolodor Street, Bucharest, Romania,  fiscal registration number  26369185

acting as Managing Authority for the Romania-Republic of Serbia IPA Cross-Border Cooperation Programme, hereinafter referred to as MA,

represented by

Mrs. UDREA Elena Gabriela, Minister

and

[organisation name],

[address: street, no., post code, town, county, country, fiscal registration number

represented by [name of legal representative] , [title]

hereinafter referred to as Lead Partner (LP), meaning the lead beneficiary, appointed by the project partners in the sense of art. 96 of the (EC) No. 718/ 2007, with its subsequent modifications and amendments

is concluded on the basis of the approved application no. [MIS-ETC code], having as legal basis:

- Council Regulation (EC) No 1085/2006 of 17 July 2006 establishing an Instrument for Pre-Accession Assistance (IPA);

- Commission Regulation (EC) No. 718/2007 of 12 June 2007 implementing Council Regulation (EC) No. 1085/2006 of 17 July 2006 establishing an Instrument for Pre-Accession Assistance (IPA), with its subsequent modifications and amendments;

- Relevant provisions of Commission Regulation (EC) No. 1828/2006 of December 2006 setting out rules for the implementation of the Commission Regulation (EC) No. 1083/2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund and of Regulation (EC) No. 1080/2006 of the European Parliament and of the Council on the European Regional Development Fund with its subsequent modifications and amendments;

- Romania-Republic of Serbia IPA Cross-Border Cooperation Programme (hereinafter referred to as Programme), approved by the European Commission on the 27th of March 2008 by Decision C (2008)1076;

- Framework agreement between the Government of the Republic of Serbia and the Commission of the European Communities on the rules for co-operation concerning EC-financial assistance to the Republic of Serbia in the framework of the implementation of the assistance under instrument for pre-accession assistance (IPA), signed on the 29 November 2007;

- Financing Agreement concluded between the European Commission and the Republic of Serbia on the 27 March 2009;

- The Memorandum of Understanding for the Romania-Republic of Serbia IPA Cross-Border Cooperation Programme, approved by the Romanian and the Serbian Government.

§ 1 Award of subsidy

1.	The object of this contract is the award of IPA financing by the MA for the implementation of the project index [project number] “[project title]”, herein referred to as “operation”, according to the decision of the Joint Monitoring Committee on 05.07.2010 in Timisoara.

2.	The Lead Partner receives funding on the basis of the provisions of the contract and its annexes, that the Lead Partner declares to know and accept.

3.	The Lead Partner accepts the funding and shall implement the part of the operation for which it is responsible in due time according to the provisions of the present contract and of the national and European legislation.

##### § 2 Duration of the contract

1.	The subsidy contract becomes effective on the date the last party signs.

2.	The implementation of the “operation” starts the day after the date when the contract becomes effective.

3.	The implementation period of the operation is …. months.

4.	During the implementation period of the operation as well as after the end of the implementation period of the operation, and for a 3 years period after the official closure of the Romania-Republic of Serbia IPA Cross-border Cooperation Programme, the Lead Partner has the obligation to preserve and to present to the Joint Technical Secretariat (JTS, within the Regional Office for Cross-Border Cooperation Timisoara, Romania), MA, Certifying Authority (CA, within the Romanian Ministry of Public Finance), Audit Authority (AA, within the Romanian Court of Accounts), European Commission (EC) and any other body designated to perform controls on the use of the financing, all operation’s documents, including the inventory for the actives/ passives resulted from using the funds..

5.	The subsidy contract ends in 5 years from the ending date of the period stipulated in paragraph 3 of this article.

§ 3 Budget of the operation

1.	Eligible amount for financing

- The total budget of the operation is …………. EUR/ [amount in letters] euro of which:

      - the total eligible value is ………… EUR (non-refundable financing and the contribution of the partner), out of which:

        - …………… EUR IPA, representing 85 %

        - …………… EUR Romanian State Budget co-financing, representing 13 % from the Romanian Partner (s) budget

        - …………… EUR Romanian Partners own contribution, representing 2 % from the Romanian Partner (s) budget

        - . …………… EUR Serbian Partners own contribution, representing 15% from the Serbian Partner (s) budget

- the non-eligible value is .. EUR , representing the total of non-eligible expenditure supported by the Lead Partner and his partners.

§ 4 Value of the contract

1.	The value of the present contract is ……………. EUR/ [amount in letters] EUR, representing the total IPA eligible value of the operation according to Annex 1 – “Budget of the operation”; MA commits itself to transfer these funds, representing 85 % of the total eligible value of the operation, to the Lead Partner.

2.	The MA will make the transfer of IPA funds in the limit of the existing balance at the date of reimbursement request, and in case of insufficient funds, payment process is suspended until the European Commission credits the Programme’s account with the amounts representing the IPA funds. If the European Commission fails to make the funds available, the MA is entitled to terminate this contract and any claim by the LP against the MA for whatever reason is excluded.

3.	The Lead Partner commits itself to support its own contribution and the non-eligible expenditures.

4.	 Any changes inside or between budget line or lines, in limit of 10% of the total budget should be made with the previous notification of the Managing Authority through the Joint Technical Secretariat, as long as the maximum amount of funding awarded remains unchanged and the goals of the operation are not affected.

5.	Contingency may be spent only with prior agreement of MA, by re-distribution to other budgetary lines and will be operated by an addendum to the present Contract.

6. 	Changes in the budget including, budget chapter, over the limit of 10% and under € 50.000 are allowed, with the previous approval of the Managing Authority through the Joint Technical Secretariat and No-objection letter from NA, through an addendum to the present contract) and as long as the maximum amount of funding awarded remains unchanged and the major goals of the operation are not affected.

7. 	As an exception, any other changes must be duly justified and shall be subject to the Programme Joint Monitoring Committee’s approval (changes of partners, changes in budget lines over € 50.000,00 etc.) and will be operated by an addendum to the present contract. In this case, the MA may decide to suspend the implementation of the project until the JMC Decision.

8.	Modifications of the contract or of the operation, that were agreed by both parties, cannot, under any circumstance, lead to the increase of the non-refundable financing value (IPA and co-financing) and/or of the percentage it represents from the total eligible value of the operation specified in article 3 paragraph 1 of the present Contract.

9.	In case that, after the ending of the implementation period of the operation, the total eligible value is lower than the eligible value stipulated in article 3 paragraph 1 a) of the present contract, the amount granted by the MA shall reduce accordingly by applying the total eligible value specified in article 3 paragraph 1 a) of the present contract. Also, at the last reimbursement claim, the eligible value of the contract will directly influence the percentages established for certain category of expenditures, so the necessary correlation will be operated.

§ 5 Eligible Expenditures

1.	Activities and related costs for the operation are eligible if they are paid in the implementation period of the operation and provided that they are necessary for the operation and are stipulated in the budget of the operation.

2.	The expenditures related to the operation are eligible provided that they respect the applicable European and national legislation in force, that they are stipulated in Annex 1 –“Budget of the operation” and provided that they comply with the terms and conditions stipulated in the present contract.

3.	Preparation costs are eligible if they were incurred after January 1st 2007 for the Romanian beneficiaries and if they incurred after the launch of the call for proposals for the Serbian beneficiaries as for the costs for preparing the technical and economic documentation, their eligibility must be in line with the provisions of the relevant national legislation.

4.	All preparation costs shall be requested for reimbursement in the first reimbursement claim.

§ 6 Advance payment and reimbursement of the expenditures

1.	An advance may be granted from the IPA funds, upon request of the Lead Partner, according to the relevant legislation and provisions of the Memorandum of Understanding, in an amount of maximum 15% from the value of the present contract. The advance payments shall be made to all Lead partners based on the IPA subsidy contract and within the limits of the IPA funds available in the accounts of the Certifying Authority. The MA shall notify when funds are available in order to submit a new advance payment.

2.	In order to receive an advance, the Lead Partner must send a request for an advance payment to the JTS as per the template in Annex 10 – “Advance request” to this contract, in maximum 10 days after signing this contract. This request shall stipulate the percentage and the amount of advance payment. The MA shall ensure the availability of advance payments on the basis of financial flows drafted on the basis of advance payment requests and within the limits of the IPA funds available in the accounts of the Certifying Authority.

3.	The MA shall verify the request for advance payment in maximum 10 days from the registration date at the MA level. The MA may suspend this deadline in case clarifications, modifications or other additional information are needed, data that must be provided by the Lead Partner in maximum 5 working days following the request. The deadline shall be recalculated from the date when the MA receives the requested information/clarifications/additional documents.

4.	The MA shall transfer the advance payment to the Lead Partner in maximum 10 days from the date of the approval of the advance payment request. The payment date is considered to be the date when the payment is transferred from the MA account to the LP account.

5. 	The LP, based on the partner’s request may transfer to each partner the advance payment received from the MA corresponding to their activities within the approved application.

6.	The advance payment will be recovered by deducting 25% from the eligible value of the next reimbursement claims from the financing source they were granted. The recovery is done starting with the first reimbursement claim in such manner that the entire advance payment shall be recovered before the last reimbursement claim.

7.	In order to comply with provisions of paragraph 6 of the present article, the MA may increase the 25% in such manner that the advance payment is entirely deducted.

8.	If the advance payment was not recovered before the final payment or before the contract is terminated, the amounts not recovered must be paid by the Lead Partner to the MA in maximum 30 days from the notification of the MA. The Lead Partner has the obligation to send to the MA a copy of the payment order, in maximum 5 working days from the paying date, in order to justify the transfer of the amounts.

9.	In case the Lead Partner does not transfer the amounts to the MA in due time, the MA may charge penalties bigger with one and a half point than the rate applied by the Central European Bank from the first working day from the month of the deadline date. Penalties are calculated to the value that has to be recovered; the final payment is done only after recovering the unduly paid amounts.

10.	The interest of the funds transferred by the MA must be transferred to the MA, because it is an ineligible expenditure.

11.	The Lead Partner may only request payments, through reimbursement claims as per Annex 11 – “Reimbursement claim”, by providing proof of progress of the operation as described in the approved application, through progress reports submitted to the first level controller, in two copies, every 3 months from the signing date of the contract. The instructions presented in the reporting models must be followed exactly.

12.	The Lead Partner must send to the Joint Technical Secretariat the reimbursement claims, together with the progress reports and all supporting documents, according to Annex 3 – “Schedule for advance and reimbursement claims”, within the deadlines set forth and based on the conditions provided hereunder and in the applicable legislation. Based on the fact that payments by the European Commission will only be made in accordance with the corresponding budget commitments and that funds can be automatically de-committed by the European Commission if the money is not spent under the relevant financial profile, the LP must request the payments as indicated in its calendar of expenditures.

13.	Even if no expenditure incurred in a reporting period, the progress report must be submitted by the Lead Partner in due time to the Joint Technical Secretariat. These reports shall be submitted in respect to the calendar of reporting taking into account the final date of eligibility.

14.	The Lead Partner must present all documents to the controllers and to make sure that all partners present their documents, in order to be verified before drafting and forwarding the reimbursement claims.

15. 	The Lead partner/partner cannot submit another control claim (for a reimbursement request) to the First level Control Unit until the previous control claim has been validated by the First Level Control.

16.	The funds will be disbursed only in Euro and will be transferred into a special account indicated by the Lead Partner. Any exchange rate risk will be borne by the LP.

17.	The Lead Partner transfers the received IPA amounts to all partners, according to the approved application, in 5 working days from receiving the amounts from the MA and shall make the proof of transfer to the MA by sending copies from the relevant bank statements, according to each contribution to the operation and will make no deduction, retention or further specific charge from the IPA amounts it receives. However, the advance payment/ first reimbursement claim will not be paid/ reimbursed to the Lead Partner by the MA before the entry into force of the Memorandum of Understanding (document signed between MA, NA, CA and AA).

18.	In case the data mentioned in Annex 3 - “Schedule for advance payment and reimbursement claims” are not observed, the Lead Partner has to inform the MA no later than in the first 15 working days of the month included in the “Schedule for reimbursement claims and progress reports”, in which the reimbursement claim should have been submitted on the reasons of the delay/other modifications and to make available a summary of the progress of the operation and the revised “Schedule for reimbursement claims and progress reports”, observing the maximum period of three months between each reimbursement claim.

19. 	Not observing the provisions of paragraph 19 will delay with 3 months the deadline for the reimbursement of expenditure.

20.	The last reimbursement request must be submitted by the LP to the JTS at the latest 31.07.2013.

§ 7 Rights and duties of the parties

Lead Partner (in compliance with art. 96 of the EC Regulation No. 718/ 2007 for each operation):

1.	The Lead Partner guarantees that it is entitled to represent all partners participating in the operation and that it will strive towards establishing with the partners the division of the responsibilities in the form of agreements.

2.	The Lead Partner is liable to the MA furthermore that he and all its partners have complied with all legal provisions and that all necessary approvals for the correct implementation of the operation have been obtained.

3.	The Lead Partner laid down the arrangements for its relations with the partners participating in the operation in an agreement (according to the Signed Partnership Agreement – Annex 4 to the present contract) including, inter alia, provisions guaranteeing the sound management of the funds allocated to the operation, including the arrangements for recovering amounts unduly paid; this partnership agreement is annex to the subsidy contract.

4.	The Lead Partner ensures the implementation of the entire operation and has to:

    - inform the MA in 5 working days calculated from the date of receiving  the documents from the partners if costs are reduced or one of the disbursement conditions ceases to be fulfilled, or circumstances arise which entitle the MA to reduce payment or to demand repayment of the subsidy wholly or in part;

    - comply with the regulations referred to in the preamble to this contract as well as with relevant national and European legislation;

    - to know and respect the provisions of the Applicant Guide (Annex 5 to the present contract)

    - request approval from the MA/JMC if the partnership, the actions or, if the budget of the operation on which this contract is based changes;

    - comply with and make sure that all partners comply with the national and European legislation on state aid, gender equality and equal opportunities, sustainable development, environmental protection;

    - respect the relevant legislation for public procurement which is mandatory for all applicants. All supplies and materials purchased under this contract must respect the provisions of art. 19 of Council Regulation No. 1085/ 2006;

    - present and to ensure that the partners present their expenditures to the controllers for verification (see § 12 of the present contract) at least 75 working days before the deadline for submitting the reimbursement claim, so that the deadline for submitting the reimbursement claim to the JTS will be met;

    - ensure that all partners submit their contributions to the reimbursement claim with at least 15 days before the deadline for submitting the reimbursement claim to the JTS;

    - ensure that all partners have a proper analytical accounting system; the accounting system must be in line with the national legislation.

    - observe and make sure that all partners observe the provisions of the Communication and Visual Identity Manuals.

5.	The Lead Partner verifies that the expenditure presented by the partners participating in the operation has been verified by the controllers.

6.	The reimbursement claim and the progress report contain information consolidated by the Lead Partner, at operation level; thus, the Lead Partner presents consolidated reimbursement claims and consolidated progress reports, being responsible for collecting documents and information from every partner.

7.	Lead Partner is liable towards the MA for ensuring that all of its partners have a legal status, that they have the capacity to manage the operation, that they respect the provisions from the Applicant’s Guide. Moreover, the Lead Partner is liable towards the MA for ensuring that its partners fulfil their obligations under this contract. The Lead Partner is also liable towards the MA for all irregularities, including those committed by the partners.

8.	The Lead Partner must answer all written requests from the MA, JTS or other bodies involved in the implementation of the programme within the deadline stipulated in the respective request. In case such request refers to additional implementation reports, the LP is responsible for gathering the information from all partners in due time.

9.	The Lead Partner takes full responsibility for the damages caused to third parties from its own fault during the implementation of the operation. MA has no responsibility for the damages caused to third parties as a result of executing the contract.

10.	The Lead Partner must not receive or have received money from other programmes for the same operation.

11.	Any results or rights related to the operation, including author’s rights and/or any other intellectual or industrial property rights, obtained from the implementation or as a result of the implementation of the contract, except the cases where such rights exist before the contract, shall represent the property of the Lead Partner and his partners, according with the partnership agreement or as the case may be.

12.	The Lead Partner cannot sell or give up in any form the goods purchased from the financing throughout the implementation period of the operation or throughout their life period, as it is stipulated by the national legislation, and 5 years after the closing date of the implementation;

13.	The Lead Partner cannot sell or otherwise transfer in any form the goods purchased from the financing throughout the implementation period mentioned in art. 2 paragraph 3 of the present contract or throughout their life period, as it is stipulated by the national legislation, if this period is smaller than the implementation period of the operation.

14.	No undue advantages should be given to other bodies and in case of investment whose costs purchase is granted, activities and ownership should be secured at least within 5 years from the operation closure.

15. 	The Lead Partner understands and agrees that the MA may delegate tasks to the JTS, according to the Implementing Agreement concluded between the JTS and therefore, the Lead Partner agrees to cooperate with the JTS in the same way as with the MA.

16.	The Lead Partner understands and agrees that following the monitoring visit the MA/JTS may propose a Plan for preventive and/or corrective measures to the LP. The JTS shall be entitled to verify the actual implementation of the Plan for preventive and/or corrective measures.

17.	The Lead Partner understands and agrees that for the projects where the Environment Impact Assessment procedure was applied it has the obligation to submit to the JTS a report regarding the effects of the project on the environment. The report shall be submitted at the same time with the progress reports and final report of the project.

18.	The Lead Partner is obliged to fill in the equal opportunities Questionnaire at the same time as the submission of the progress reports and final report.

19.	The Lead Partner understands and agrees that templates for the report regarding the effects of the project on the environment and the equal opportunities Questionnaire shall be provided to the LP after signing the subsidy contract with the MA. Information necessary to fill in the report regarding the effects of the project on the environment and the equal opportunities Questionnaire concerns all the aspects of the implementation of the project.

20.	The Lead Partner understands and agrees that the final report regarding project implementation must be submitted to the JTS at the same time with the final reimbursement claim, but no later than 31.07.2013 The final report shall comply with the three months reporting period, as for all other progress reports.

Managing Authority

      - The MA shall make available the information regarding the official closure date of the Programme to the Lead Partner in maximum 5 working days from the date of the receipt of the European Commission’s official notification.

      - The MA has the right to decide on the eligibility of expenditure related to the reimbursement claims.

      - The MA has the obligation to support the Lead Partner by providing necessary information and clarifications for the implementation of the operation.

      - The MA has the obligation to reply to any written solicitation from the Lead Partner in maximum 30 days from the date the MA receives the request.

      - The MA ensures the technical and financial monitoring of the operation.

      - The MA shall authorize all eligible expenditures related to the reimbursement claims submitted by the Lead Partner.

      - The MA has the obligation to inform the Lead Partner regarding the reports, conclusions and recommendations made by the European Commission that may affect the implementation of the present contract.

      - The MA shall reimburse the expenditures according to the provision in Annex 3 – “Schedule for advance payment and reimbursement claims” and Annex 6 – “Reimbursement of expenses Guidelines”.

      - In case one of the obligations of the Lead Partner are not fulfilled, the MA may suspend the execution of the contract.

      - In case of suspending the contract, the MA notifies the Lead Partner regarding this decision, duration of the suspension period, the proposed corrective measures and also the related financial measures. The MA also notifies the Lead Partner when the suspension period is finished. The MA shall also notify the Lead Partner if the suspension period is cancelled prior to the initially set deadline.

      - The MA may delegate tasks to the JTS, according to the Implementing Agreement concluded between MA and JTS, therefore the JTS may act in the name and on behalf of MA.

      - Following the verification visit to assess the actual implementation of the MA/JTS Plan for preventive and/or corrective measures, the MA may enforce sanctions on the LP according to the gravity of the situation, should it find out any failure to comply with its application.

§ 8 Information and publicity

1.	The Lead Partner must inform itself and must inform that its partners inform the public, by means of the measures laid down in article 62 of the Regulation 718/2007, about the assistance obtained from the IPA funds.

2.	The Lead Partner is responsible for the implementation of the information and publicity activities related to the non-reimbursable financial assistance received through the programme

3.	The Lead Partner must ensure and must satisfy itself that all partners ensure transparency and accurate information to the mass media on the projects financed under the Romania-Republic of Serbia IPA Cross-border Cooperation Programme.

4.	All information and publicity actions developed by the partners (including the Lead Partner) must observe the Communication and Visual Identity Manuals applicable to the Programme (available on the Programme website www.romania-serbia.net or on request at the Joint Technical Secretariat).

6.	For all information and publicity actions developed by the partners, the Lead Partner must ensure that they archive in a single place (hard copy and/or electronically) the documents related to these activities (eg: information and publicity materials they produced: printed materials, audio-video materials).

7.	The Lead Partner is responsible to inform the JTS regarding the information and publicity measures taken in order to promote the operations financed under IPA.

8. 	The MA shall be authorised to publish, in whatever form and/ or by whatever medium, including the Internet, the following information:

a) the name of the LP and its partners;

b) the purpose of the subsidy and projects outputs;

c) the amount granted and the proportion of the total eligible cost of the operation accounted for by the funding;

d) the geographical location of the project;

e) information and communication materials produced within the project;

f) any other information agreed with the LP.

9.	The rules stipulated in the Communication and Visual Identity Manuals are mandatory for all project partners.

§ 9 Confidentiality

1.	The MA and the Lead Partner undertake to preserve the confidentiality of any document, information or other material communicated to them in confidence until at least 5 years from the official closure of the programme.

2.	As an exception from the rules provided in the previous paragraph, the data used for publicity purposes for informing on and promoting the use of IPA funds shall not be considered as having confidential status.

3.	Releasing any information to persons involved in implementing/ verifying/ controlling/ auditing the operation shall be performed on confidential basis and shall only cover the information that is necessary for implementing the contract.

4.	The contracting party shall bare no responsibility for releasing information on the contract if:

  - the information was released with the written agreement of the other contracting party; or

  - the contracting party was legally forced to release the information.

5.	Failing to observe the confidentiality obligation gives the damaged party the right to claim compensations from the damaging party.

§ 10 Conflict of interests

1.		In the present Contract, the conflict of interests represents any circumstances that have affected or may affect the execution of the Contract by the parties, in an objective and impartial manner. Such circumstances may result from economic interests, political or national preferences or family connections.

2.		The parties take upon themselves to take all necessary measures in order to avoid any conflict of interests and to keep each other informed, in up to 5 (five) days from finding out, on any circumstances that have generated or may generate such a conflict. Any conflict of interests that arises during the implementation of the contract shall be immediately notified to the JTS. The MA reserves the right to verify such circumstances and take the necessary measures, where necessary.

§11 Irregularities and reimbursement of the funding

1.		“Irregularity” according to the current Contract is any derogation from the law, regulation and compliance with the provisions of the memorandums of understanding, financing agreements regarding the Community funds and related co-financing, as well as with the provisions of the contracts concluded according to these memorandums/agreements, which by a ineligible expenditure prejudices the general budget of the European Communities or the budgets these manage in their name and/or the budgets granting the related co-financing.

2.		In case of irregularity, the MA may impose to the Lead Partner, in written, within 5 (five) working days from the discovery of the irregularity, all the necessary measures for the elimination or diminishing of the consequences on the implementation of the operation.

3.		In case an irregularity is committed, the Lead Partner is responsible for reimbursing the entire amount to the MA, even if the irregularity was committed by one of the partners.

4.		MA may suspend or terminate the contract in the case the partners fail to take the measures imposed.

5.		The MA takes the decision for suspending/terminating the contract, after verifying the reasons presented by the Lead Partner and/or JTS and the related documents.

6.		In case the contract shall be terminated, the MA notifies the Lead Partner regarding this decision and the related financial measures. In this case, the MA will request that within 30 days as of the receiving date of the notification, the Lead Partner shall return the amounts that the notification refers to, including the bank charges.

7.		For the irregularities committed by a partner, the Lead Partner is entitled to request these amounts from the responsible partner in order to pay them to the MA.

8.		If the Lead Partner does not manage to recover the unduly paid money from the partners, he will inform the MA and will send it all necessary documents for the MA to be able to take all necessary measures stipulated by the legislation in force.

9.		Any extra payment done by the MA is considered unduly paid amount, and the Lead Partner has to repay the respective amounts in 30 days from the receiving date of the notification from the MA.

10.		In case the irregularity is discovered before the final payment, the MA may decide the diminishing of the reimbursed amount starting with the next payment until the total recovery of the debt, to which it is added the bank charges.

11.		In case the irregularity resulting in an unduly paid amount is discovered after the final payment and the debt was not entirely recovered, the MA shall notify the Lead Partner regarding the unduly paid amount, and the Lead Partner has the obligation to return, in 30 days from the receiving date of the notification, the amount, including bank charges.

12.		Starting the 31st day from the deadlines stipulated at points 6,9,11 an interest rate bigger with one and a half points than the rate applied by the Central European Bank as in force on the first working day from the month of the deadline date shall be applied to the owned amounts.

13.		The LP shall pay the bank charges resulted from the reimbursing of the amounts to the MA.

14.	The National Authority, in close cooperation with the Managing Authority, will be engaged in the implementation of all relevant prevention, detection and correction measures related to irregularities on the territory of the Republic of Serbia.

§ 12 Audit, control and evaluation of the operation

1.	The responsible auditing bodies of the EU and the two partner states and, within their responsibility, the Audit Authority from Romania and the group of auditors as well as the MA are entitled to audit the proper use of funds by the Lead Partner or by its partners or arrange for such an audit to be carried out by authorized persons.

2.	A first level control system has been established both in Romania and Republic of Serbia in order to check the expenditure made by the project partners from each country. Therefore, each partner has the obligation to ensure that its expenditures are checked and validated by a controller from the state on whose territory it is located, before the reimbursement request is submitted.

3.	The MA is entitled to verify and to control the proper use of funds by the Lead Partner or by its partners. The verifications to be carried out by the managing authority shall cover administrative, financial, technical and physical aspects of operations, as appropriate.  The MA shall be responsible for the control of the proper use of funds by the Lead Partner or by its partners, in particular through preventing, detecting and correcting irregularities and recovering amounts unduly paid together with interest on late payments where appropriate.

4.	The Lead Partner will provide all documents required for the audit, control or evaluation, provide necessary information and give access to the premises. The Lead Partner and its partners are at all times obliged to retain for audit and control purposes all files, documents and data about the operation for a minimum period of 3 years after the closure of the Romania-Republic of Serbia IPA Cross-Border Cooperation Programme. The documents must be properly archived. Also, the MA must be informed on the location of these documents.

5.	In case the Lead Partner/ partner organisation cease to exist, all documents related to the operations/ parts of operations implemented shall be hand over to the JTS for retention purposes, for a minimum period of 3 years after the closure of the Romania-Republic of Serbia IPA Cross-Border Cooperation Programme. The documents must be properly archived. Also, the MA must be informed on the location of these documents.

6.	The Lead Partner must have separate accounts for the operation, according to the national legislation.

7.	The Lead Partner is obliged to guarantee that both the Lead Partner and all of its partners fulfil the duties stipulated above.

8.	The recommendations received after an audit, control must be observed, otherwise the MA has the right to terminate the contract.

§ 13 Assignment, legal succession

1.	The Lead Partner cannot renounce totally or partially the rights and obligations resulted from the present contract, unless he has the clear agreement of the MA and of the JMC.

2.	In case of legal succession, e.g. where the Lead Partner changes its legal form, the Lead Partner is obliged to transfer all duties under this contract to the legal successor. The Lead Partner shall notify the MA about any change with 15 working days beforehand.

§ 14 Amendment

1.	Any modification to the present contract is made only with the agreement of both parties and takes the form of an additional act to the present contract.

2.	As an exception from the provisions of paragraph 1, the Lead Partner may make the following changes, with the notification of the MA

a) Any changes inside or between budget line or lines, in limit of 10% of the total budget should be made with the previous notification of the Managing Authority through the Joint Technical Secretariat, as long as the maximum amount of funding awarded remains unchanged and the goals of the operation are not affected.

b) Changes in the Annex 3 - “Schedule for advance and reimbursement claims” may be done only with the prior notification of the MA. The MA has to be notified with at least 30 days before the next payment claim is due to be submitted;

c) Change of headquarter may be done and shall be forwarded to the MA within 15 days following the change of address.

3.	The parties have the obligation to inform on the initiation to amend the present contract with minimum 30 days before the additional act produces its effects.

4.	Addenda become effective in the next day after their signing by the last party, except the case when by the addendum are confirmed modifications in the national/ European applicable legislation with impact on the implementation of the contract, modifications that become effective from the date the respective legal acts become effective.

§ 15 Termination

1.	Any breach of the provisions of the present contract may result in the termination of the present contract and in the reimbursement of the financing and the repayment of unduly paid amounts.

2.	In exceptional and duly justified cases, including the occurrence of “Force majeure” the MA may decide on terminating the contract, by a written notification, without requesting the reimbursement of the already paid amounts.

3.	The MA is entitled to terminate this contract, without any other formality, and to demand repayment of the amounts already paid amounts, if:

- The MA finds an inconstancy between the reality and the declarations of the Lead Partner in the application form, regarding the financing of the operation from national or European public funds, or regarding the financing from other national or European programmes;

or

- The MA finds that the subsidy awarded has been partially or entirely misapplied for purposes other than those agreed upon;

or

- The MA finds that insolvency proceedings are instituted against the assets of the Lead Partner or insolvency proceedings are dismissed due to lack of assets for cost recovery, provided that this appears to prevent or risk the implementation of the operation,

or

- the Lead Partner closes down;

or

- The MA finds that, during the implementation period of the operation, including 5 years after the closing of the implementation period mentioned in art. 2 paragraph 4, the Lead Partner wholly or partly sells, leases or lets the operation/goods purchased from the financing to a third party;

or

- The MA decides that the operation is no longer eligible, if during its implementation appear modifications that affect the implementation conditions/ create for a third party an unjustified advantage, and if the modification is the result of a change in the nature of the property/ ceasing/ change of the location of the operation;

or

- The MA finds that the Lead Partner did not notify the MA in the deadline on a case of conflict of interests or the necessary measures for ending such a situation were not taken; or

4.	The MA is entitled to terminate this contract if:

- the operation has not been or cannot be implemented in a manner that the MA considers appropriate with the goal of the operation; or

- the Lead Partner has failed to submit in the deadlines required reports or proofs, or to supply necessary information, in the deadline and has not justified these delays; or

- the Lead Partner or the partners has/have impeded or prevented the auditing; or the recommendations resulted from the audit missions are not respected;  or

- an irregularity is discovered at the Lead Partner/partner level; or

- the Lead Partner has failed to fulfil any other conditions or requirements stipulated in this contract or in the time required by the MA through the notification; or

- the Lead Partner did not submit a reimbursement request for two consecutive deadlines as mentioned in the Annex 3 - “Schedule for advance payments and reimbursement claims”.

5.	If the MA exercises its right of termination, the Lead Partner is obliged to transfer the repayment amount to the MA. The repayment amount is due within 30 days following the date of the letter by which the member state asserts the repayment claim; the due date will be stated explicitly in the order for recovery. In case of non-payment at the due date, penalties bigger with one and a half point than the rate applied by the Central European Bank from the first working day from the month of the deadline date applied to the owned amounts, shall be paid. These penalties will not be supported from the contract value (they are non-eligible expenditure).

6.	If any of the circumstances stipulated at paragraph 3 of the present article appear before the entire amount of the subsidy is paid to the Lead Partner, the payments will cease and there will be no reimbursement claims submitted by the LP for the rest of the amount.

###### § 16 Force majeure

1.	According to the present contract, the “Force majeure” represents any unpredictable and insurmountable event, occurred after the signing of the present contract and that prevents the total or the partial execution of the contract. There are considered cases of “force majeure”: wars, natural calamities, epidemics and other similar events.  The “force majeure” exonerates the parties of the responsibility for not executing partially or totally the obligations stipulated in the present contract during the period they appear and only if the events were properly notified. It is not considered to be “force majeure” a event similar to those present above, that, without creating an impossibility of execution, makes the execution of the obligations very expensive for one of the parties.

2.	The party that states that it is a case of “force majeure” has the obligation to notify the other party in 5 days from the date of the case of “force majeure” and to prove the existence of the reality of this situation in 15 days. In case the “force majeure” stops. The event must be notified to the other party in 5 days.

3.	The responsible party will support all costs if the notification procedure is not observed.

4.		The execution of the contract is suspended during the period of “force majeure”

5.		In case the contract must be suspended from this reason on a period longer than three months, the MA has the right to decide the continuation/modification/termination of the contract.

§ 17 Correspondence

1.		To the effect of this agreement, the partners shall choose headquarters at the address mentioned below where any official notifications can be lawfully served:

a.	Ministry of Regional Development and Tourism (MRDT), located in Bucharest,  17 Apolodor Street, North Side, sector 5, Telephone no.: +40 372 111 367, Fax no.: +40 372 111 431, fiscal registration number 26369185 (as MA)

b.	Regional Office for Cross Border Cooperation Timişoara (ROCBC) located in Timişoara, 5 Proclamaţia de la Timişoara Street, Telephone no.: +40 356 426 360

Fax: +40 356 426 361, (for the JTS)

c.	[name of beneficiary], . [address: street, no., post code, town, county, country] , post code ..............., telephone: ..................., fax: ..............................., e-mail:..........................., fiscal registration number: .................. (as Lead Partner)

2.		All correspondence between the MA and the Lead Partner shall be done through the JTS, in English.

3.		Any change of address shall be forwarded to the other party of this contract within 15 days following the change.

§ 18 Final provisions

1.	In case a dispute arises between the MA and the Lead Partner, regarding the implementation of the present contract, a friendly conciliation shall be attempted. In case no mutual agreement can be reached, the competent legal authorities from Bucharest shall solve the dispute.

2.	Romanian law governs the present contract.

3.	The present contract forces the parties to observe in all and with good faith each provision, according to the principle of the bindery legal force of the contract between parties.

# § 19 Signatures

1.	This Subsidy Contract is issued in 4 original copies, in English language, one for the LP, one for the MA, one for NA and one for the JTS.

Annexes

Annex 1: 		Budget of the operation

Annex 2: 		Approved application form

Annex 3: 		Schedule for advance payment and reimbursement claims

Annex 4: 		Partnership Agreement

Annex 5: 		Applicant’s Guide

Annex 6:  		Reimbursement of Expenditures Guidelines

Annex 7: 		Monitoring Measures

Annex 8: 		Method of calculation for general administration costs

Annex 9: 		Time-sheet

Annex 10:		Advance request

Annex 11:		Reimbursement claim

Annex 13: 		Progress report

Annex 14:		Addendum

| ###### Managing Authority | ###### Lead Partner |
| --- | --- |
| Legal representantive: Minister Name: UDREA Elena Gabriela | Legal representative: [title of the legal representative] Name: .................................... |
| Signature: Date: | Signature: Date: |

| ###### National Authority |  |
| --- | --- |
| Legal representantive: Name: |  |
| Signature: Date: |  |

Budget of the operation comprises: General Budget, Detailed Budget, Financing Sources, Budget per activity and Estimated Eligible Expenditure Calendar. Chapter IV-General project budget comprises all costs from Chapter IV-Detailed Budget and vice-versa. Own contribution from “Financing sources” comprises both the 2% for the Romanian beneficiaries and the 15% for the Serbian beneficiaries calculated based on each partner budget.

Applicable only for investment projects